## Conference Project Charter
Select
|  | PROJECT CHARTER: Cyclops | [5 empty] | Project Management & Implementation
Installation
Select
Project Start/End |  |  |  | Document Amendment Record |  |  |  | 2
Project Start Date: |  | 07/21/2024 |  | Change No. | Date | Prepared by | Brief Explanation
Project End Date: |  | 07/28/2029
Customer and Resource Information
Project Name: |  | Network Optimization |  | PO#: |  |  | SO#:
Requestor Name: |  | Assigned by client company |  | E-mail: |  |  | Mobile:
Client Project Manager: |  | Assigned by client company |  | E-Mail: |  |  | Mobile:
Project Manager |  | Assigned by our company |  | E-Mail: |  |  | Mobile:
Program Manager: |  | Assigned by our company |  | E-Mail: |  |  | Mobile:
Project Scope
Project Description: |  | The project aims to develop an adaptable spectral analysis platform integrating AI-enabled technologies, designed for military operations and biotechnological applications. The platform will significantly enhance sensing capabilities, improve analytical accuracy, and facilitate data-driven decision-making processesDevelopment and integration of AI-assisted spectral analysis methods for accurate signal detection in military settings and dependable functional biomolecule analysis in biotechnological applications
Project Objectives: |  | Define operational and scientific requirements for spectral analysis in military and biotechnological contexts. Develop and integrate spectral analysis technologies (suitable sensors such as UV-Vis, NIR, Raman, mass spectrometry as well as spectrometer analyzer) capable of detecting and characterizing chemical, biological, radiological, nuclear, and explosive (CBRNE) threats Integrate sensors into a unified platform capable of multi-sensor data fusion and real-time spectral data acquisition Develop adaptive algorithms for spectral data processing, anomaly detection, classification, and pattern recognition Specify performance metrics, including sensitivity, spectral range, data processing speed, and environmental conditions for biomolecular analysis, including protein characterization, DNA sequencing, metabolomics, and environmental monitoring Validate and demonstrate the effectiveness of the developed platform through testing in laboratory and field environments. Regulatory approval - Adhere to relevant regulatory standards and guidelines applicable to military operations, biotechnological applications, data handling, and biosafety.
Customer Needs and Requirements
Project Life Cycle Stages
1) Initiation: |  | -Look into previous intellectual properties (IP) and patents. Determine if it is feasible technologically and has market demand. Determine the areas where freedom to operate is present. -Study the top AI-based software product lines of major companies (Keysight, Rohde & Schwarz, Anritsu, CRFS and Signal Hound). -Examine websites (e.g., Sam.gov) to determine current contract tender trends. -Document the purpose of developing a versatile spectral analysis platform. Include objectives like improving sensing and analytical capabilities, the scope of the project (military and biotechnological applications), initial estimates of time and budget, and key milestones. -Present findings to sponsors and stakeholders. Sponsor and 70% of stakeholder agreement required to proceed. -Assemble a team with expertise in spectral analysis, military technology, biotechnology, and project management to ensure effective development and integration of the platform.
2) Planning: |  | -Draft scope statement, and confirm project scope and objectives with clients. -Develop realistic cost, schedule, and performance estimates. -Establish a plan for changes and communication. -Make sure that key stakeholders and key requirements have been identified and communicated. -Make plan for conducting feasibility study, performing risk assessment, and contingency plans, establish supply chain strategy where needed -Develop WBS for reviewing schedule, budget, and resource allocation with key stakeholders -Establish what - if scenarios and outsourcing options -Develop/ review quality assurance plan, a plan for initial design (prototyping), review and approve planning documents
3) Executing: |  | -Phase 1: Start development of the spectral analysis platform and allocate resources to the teams. Train AI models with input data (e.g., biological or signal) for enabling the generative AI engine to recognize patterns, establish correlations, and establish predictive models -Phase 2: Research and develop new spectral analysis techniques that improve the accuracy and decision making capabilities of the AI platform. Create the prototypes of the spectral analysis device in military and biotech applications. -Phase 3: Consult with the lawyers to secure a proper End User License Agreement to protect the IP of the biotech firms using our platform. -Deliverable 1: Ensure Cyclops can analyze data, reliably predict the outcome, and make informed decisions. Ensure the AI model is trained to detect and distinguish radio transmitters within specific distance range (e.g., 50 m) Ensure platform to generate high resolution differential absorbance spectrum Ensure platform to enable detection and comparison of structural changes Ensure platform to enable sampling at low vol and wide concentration range Ensure that AI model is trained for designing drug or detecting biomolecules in complex biological system -Phase 4: Create all necessary training guides for military and biomedical applications to enable staff training. Conduct pilot testing at every deliverable phase completion point, troubleshooting all errors that arise.
4) Monitoring & Controling |  | - Perform comprehensive testing and calibration to ensure system functionality, accuracy, reliability, and robustness. Identify key parameters and validate the platform with field tests and simulations, then fine-tune parameters and address issues based on findings. - Identify and prioritize new risks, develop mitigation strategies, and maintain an issue log. Evaluate AI prediction accuracy and promptly establish a clear process for escalating and resolving issues. Regularly review and update risk plans with stakeholders. - Ensure spectral analysis techniques meet quality standards through inspections, testing, and reviews. Track metrics, address deviations quickly, document activities, and update stakeholders to maintain compliance and improvements.
5) Closing |  | -Prepare detailed technical documentation, including system architecture diagrams, hardware specifications, software configurations, and algorithm descriptions -Verify the project deliverables in accordance with the specified requirements -Marketing collateral (if needed). Assurance that all the work has been completed. Assurances that all agreed upon PM processes have been executed. Gain signed recognition of completion of the project.
Project Priorities
1) Feasibility Study 2) Technical development/refinement 3) Go to market plan
Project Scope Status
Within Scope: |  | An AI powered software framework capable of being trained in the following (Minimum Viable Product): - Learning and categorizing of data comprising of IQ captures of low-frequency RF signals and images from high frequency X-rays - Making location predictions via TDoA (Time Difference of Arrival) for unknown radio signal sources - Ability to directly control spectrum analyzers from Keysight, Rodhe & Schwarz and Anritsu using SCPI commands (if available) - Creating a user customizable GUI interface for main application categories: Military field use, Clinical Studies, Biological Research - Create a licensing and scalable support structure based on key customer segments - Preliminary clinical studies in line with provided quidline and specifications
Out of Scope: |  | External partners will manage the complete pre-clinical and clinical studies to verify the efficacy and safety of the designed biomolecules, while Cyclops will oversee a limited portion of the pre-clinical work, also with the support of external partners The production of spectroscopy technology is accomplished with the assistance of an external manufacturing partner. External partners will handle incorporation of the AI-platform into the large scale manufacturing setting for reliable quantification of target biomolecules for making informed decision Software updates will be delivered after launch, therefore out of scope for launch. Non-terrestrial signals, with the exception of GPS, will be considered out of scope and not available as part of the AI training for initial launch. Underwater, low frequency signals such as those to communicate with deployed submarines. Support for acoustic analysis such as sound, sonar and ultrasound. Multi-language support not available for initial launch Cloud storage is not available due to HIPAA and military operational security concerns. Clinical studies will be outsourced and not conducted by the core project team. Engaging regulatory agencies outside of the U.S for initial launch.
Project Key Points Confirmation
Place: San Jose, CA
Time/period: 5 years
Budget: $50,000,000
Project Assumptions
Data Availability: Sufficient high-quality spectral data for training and validating AI models will be accessible for both military and biotechnological applications.
Regulatory Compliance: Necessary approvals will be obtained in a timely manner by the external partners.
Resource Availability: Adequate resources, including skilled personnel and hardware infrastructure, will be available throughout the project lifecycle.
Stakeholder Support: Key stakeholders, including military and biotechnological partners, will provide necessary support and collaboration for successful project execution.
No severe economic downturns/interest rate hikes above nominal levels/tax changes
Project Deliverables
No. | Deliverable Description | [5 empty] | Planned Date
1 | The Cyclops software/hardware platform can analyze, make predictions and report relevant data to military users and biotech professionals after being fed training data. | [5 empty] | 2025-07-21
2 | Detect, identify and pin-point location of unknown RF signal (military use-case) | [5 empty] | 2025-12-31
3 | AI-powered spectroscopy technology for reliable analysis of biomolecules of interest in different biotech applications, including complex biological mixture and tissues | [5 empty] | 2027-12-31
4 | GUI for end-user | [5 empty] | 2028-12-31
5 | Initial release of software with marketing collaterals | [5 empty] | 2029-07-28
6 | User Training Materials/Troubleshooting Guides | [5 empty] | 2029-07-28
Project Risks
No. | Risk Description | [5 empty] | Impact (H, M, L)
1 | AI-generated proteins may pose unknown risks, including unintended biological effects or allergenicity. Assessing and mitigating these risks is crucial for regulatory approval. | [5 empty] | M
2 | Analysis of large amount of data to identify patterns and relationship that may not be apparent to humans | [5 empty] | H
3 | The intellectual property landscape surrounding AI-generated proteins can be complex. There may be disputes over patents related to the AI models | [5 empty] | M
4 | Protecting proprietary data used to train AI models, including confidential biological information, is essential for maintaining competitive advantage | [5 empty] | L
5 | Regulatory guidelines specific to AI-generated proteins may be lacking or still under development. | [5 empty] | H
6 | Ethical consideration ensuring that AI technologies are used ethically and responsibly is crucial. | [5 empty] | H
7 | Regulatory approval process can be complex and lengthy. AI-generated proteins may face additional scrutiny due to their innovative nature. | [5 empty] | M
8 | Coordination Among Stakeholders Effective regulation of AI-generated proteins requires collaboration among various stakeholders, including regulatory agencies, researchers, and industry experts. | [5 empty] | L
9 | Finding reliable external partners for manufacturing the device and conducting pre-clinical studies, as well as for large-scale platform validation and clinical studies, is a challenging task | [5 empty] | H
10 | Competing technologies with similar applications may pose risks | [5 empty] | M
REVIEWS AND APPROVALS
Section Reviewed |  | Reviewed by (Name) | Reviewed by Position |  |  | Date Reviewed | Approved (Y/N)
Project Charter |  | Ali Abghari | Project Lead |  |  | 2024-08-08 | Y
Project Plan & WBS |  | Toan Vo | Project Lead |  |  | 2024-08-08 | Y
APPROVAL AND SIGN-OFF
CUSTOMER APPROVAL |  |  |  | COMPANYs APPROVAL
Name: |  |  |  | Name:
Title: |  |  |  | Title:
Signature: |  |  |  | Signature:
Date: |  |  |  | Date: